## Velocity Tracker
Sprint | Sprint Goal | Start Date | End Date | Committed SP | Completed SP | Velocity | Status
Sprint 1 | Environment setup, DB schema, user stories sign-off, buyer/seller registration & login, Angular landing page | Mar 19, 2026 | Apr 01, 2026 | 28 | 26 |  | Completed
Sprint 2 | JWT authentication, role-based security, predictive alerts, user/pharmacy profile edit, JWT interceptor fix | Mar 31, 2026 | Apr 10, 2026 | 34 | 34 |  | Completed
Sprint 3 | Admin enhancements, pagination across all views, Vitest unit tests, E2E tests, security cleanup, dark mode polish | Apr 13, 2026 | Apr 24, 2026 | 32 | 30 |  | Completed
Sprint 4 | PETZ Testing — 20 test scenarios + 50 test cases authoring, sprint planning, velocity documentation | Apr 27, 2026 | May 08, 2026 | 36 | In Progress |  | In Progress
Metric |  |  |  | Value
Average Velocity (Sprint 1–3)
Sprint 4 Projected Velocity
Total Story Points Committed (Sprint 1–4)
Total Story Points Completed (Sprint 1–3)
Sprint 4 Committed Story Points
Completion Rate — Sprint 1–3 Average

## Product Backlog
US ID | Epic | User Story | Acceptance Criteria (Summary) | Story Points | Priority | Linked Scenario | Sprint | Status
US-001 | Auth & Session | As a citizen, I want to receive an OTP on my phone so that I can log in without a password | POST /auth/send-otp returns 200 for valid +91 number; 400 for missing country code; 429 after 5 requests/hour | 3 | High | PETZ_TS_01_OTP_Auth | Sprint 4 | To Do
US-002 | Auth & Session | As a citizen, I want to verify my OTP so that I receive a REPORTER session token | POST /auth/verify-otp returns JWT (isTemporarySession:true, role:REPORTER) for correct 6-digit OTP; 400 for wrong or short OTP | 3 | High | PETZ_TS_01_OTP_Auth | Sprint 4 | To Do
US-003 | Auth & Session | As a citizen, I want to use a missed-call fallback so that I can authenticate even if SMS fails | Missed-call link navigates to /sos/auth/missed-call; verification flow completes successfully | 2 | Medium | PETZ_TS_01_OTP_Auth | Sprint 4 | To Do
US-004 | Auth & Session | As a new user, I want to register a full account so that I can access adopter features | POST /auth/register creates ADOPTER; duplicate email/phone returns 409; weak password returns 400; ADMIN role blocked | 3 | High | PETZ_TS_02_Registration_Login | Sprint 4 | To Do
US-005 | Auth & Session | As a registered user, I want to log in with email or phone + password so that I can access my account | POST /auth/login returns JWT for valid credentials; 401 for wrong password; 423 after 5 failures; 15-min auto-unlock | 3 | High | PETZ_TS_02_Registration_Login | Sprint 4 | To Do
US-006 | Auth & Session | As a temporary REPORTER, I want to convert my session to a full account so that I retain my rescue history | POST /auth/convert-session upgrades REPORTER JWT; full account login works with new credentials | 2 | High | PETZ_TS_03_SessionAndProfile | Sprint 4 | To Do
US-007 | User Profile | As an authenticated user, I want to view my profile so that I can see my current details | GET /users/me returns id, role, fullName, phone, email, phoneVerified, emailVerified, active, lastLoginAt; 401 without token | 2 | High | PETZ_TS_03_SessionAndProfile | Sprint 4 | To Do
US-008 | User Profile | As an authenticated user, I want to update my name, email, and phone so that my details stay current | PATCH /users/me updates fields; changing email/phone resets verified flag to false | 2 | Medium | PETZ_TS_03_SessionAndProfile | Sprint 4 | To Do
US-009 | User Profile | As an authenticated user, I want to change my password so that I can keep my account secure | POST /users/me/password succeeds with correct current password; old password rejected after change; wrong current password returns 400 | 2 | Medium | PETZ_TS_03_SessionAndProfile | Sprint 4 | To Do
US-010 | User Profile | As a user, I want to upload a profile photo so that my account has a recognisable avatar | POST /users/me/photo accepts JPEG/PNG <=20 MB; returns non-null profilePhotoUrl; >20 MB returns 400/413 | 1 | Low | PETZ_TS_03_SessionAndProfile | Sprint 4 | To Do
US-011 | Notifications | As a user, I want to see a paginated notifications list so that I can review all platform alerts | GET /users/me/notifications returns newest-first paginated list; unreadOnly=true filters correctly; unread-count is accurate | 2 | Medium | PETZ_TS_04_Notifications | Sprint 4 | To Do
US-012 | Notifications | As a user, I want to mark notifications as read and delete them so that I can manage my inbox | PATCH /{id}/read marks single; PATCH /read-all marks all; DELETE removes notification (404 on re-fetch); cross-user access returns 403 | 2 | Medium | PETZ_TS_04_Notifications | Sprint 4 | To Do
US-013 | SOS Reporting | As a citizen, I want to submit an SOS report with urgency level and location so that help can be dispatched | POST /sos-reports accepts CRITICAL/MODERATE/LOW; boundary coordinates validated; missing fields return 400; 3/hour rate limit enforced | 3 | High | PETZ_TS_05_SOSReportCreation | Sprint 4 | To Do
US-014 | SOS Reporting | As a reporter, I want to attach photos and videos to my SOS so that rescuers understand the situation | POST /sos-reports/{id}/media accepts JPEG/PNG/MP4; 3-photo cap; 1-video cap; >20 MB rejected; all URLs returned on GET | 2 | High | PETZ_TS_06_SOSMedia | Sprint 4 | To Do
US-015 | NGO & Rescue | As an NGO representative, I want to register my NGO so that it can be assigned rescue missions | POST /ngo/register creates NGO (isVerified:false); second registration returns 409; unverified NGO hidden from public browse | 3 | High | PETZ_TS_07_NGO_Registration_Mission | Sprint 4 | To Do
US-016 | NGO & Rescue | As an NGO volunteer, I want to update a rescue mission status so that the platform tracks progress | PUT /rescue-missions/{id}/status transitions DISPATCHED to ON_SITE to TRANSPORTING to COMPLETED; summary stored; admin verify closes case | 3 | High | PETZ_TS_07_NGO_Registration_Mission | Sprint 4 | To Do
US-017 | NGO & Rescue | As a volunteer on-site, I want to record arrival, assess the animal, and find nearby hospitals | PATCH /rescue/{sosId}/arrival marks ON_SITE; POST /assessment stores condition; GET /hospitals/nearby returns sorted emergency list | 3 | High | PETZ_TS_08_OnSiteRescue | Sprint 4 | To Do
US-018 | NGO & Rescue | As a vet, I want to receive a handover and confirm animal release so that the case can be closed | POST /alert and /booking create emergency record; POST /handover requires VET/ADMIN role (403 for REPORTER); POST /release confirms closure | 3 | High | PETZ_TS_08_OnSiteRescue | Sprint 4 | To Do
US-019 | Hospitals | As a citizen, I want to browse verified hospitals sorted by distance so that I can find the nearest help | GET /hospitals without auth returns verified-only; lat/lon sorts by distanceKm; disabled/unverified excluded | 2 | High | PETZ_TS_09_HospitalDiscovery | Sprint 4 | To Do
US-020 | Hospitals | As a user, I want to search hospitals by city, service type, and availability so that I can filter results | GET /hospitals/search filters by city, emergencyReady, openNow, serviceType; full profile returns services and doctors | 2 | High | PETZ_TS_09_HospitalDiscovery | Sprint 4 | To Do
US-021 | Hospitals | As a hospital admin, I want to create and manage appointment slots so that patients can book sessions | POST /hospitals/slots requires HH:mm:ss format; recurring slots created for specified days; blackout locks AVAILABLE (not BOOKED) slots | 3 | High | PETZ_TS_10_SlotManagement | Sprint 4 | To Do
US-022 | Hospitals | As a patient, I want to lock and confirm an appointment slot so that my booking is reserved | POST /lock returns lockedUntil (+2 min); POST /confirm creates CONFIRMED appointment; slot becomes BOOKED; lock expiry and double-booking prevented | 3 | High | PETZ_TS_11_BookingFlow | Sprint 4 | To Do
US-023 | Hospitals | As a patient, I want to cancel or reschedule an appointment so that I can adjust my plans | PATCH /cancel frees slot (irreversible); PATCH /reschedule swaps slots; attend/complete with clinical notes updates pet record; no-show tracked | 3 | High | PETZ_TS_12_AppointmentLifecycle | Sprint 4 | To Do
US-024 | Admin | As an admin, I want to approve or reject hospital registrations so that only verified hospitals are public | GET /admin/hospitals/pending lists pending; APPROVE sets isVerified:true; REJECT rejects; DISABLE cancels bookings + notifies; 403 for non-admin | 3 | High | PETZ_TS_13_HospitalAdminActions | Sprint 4 | To Do
US-025 | Adoption | As a citizen, I want to browse adoptable pets so that I can find a pet to adopt | GET /adoptable-pets without auth returns only LISTED pets; distance sort; size=100 max; ADOPTED/ARCHIVED excluded | 2 | High | PETZ_TS_14_AdoptablePetsBrowse | Sprint 4 | To Do
US-026 | Adoption | As a citizen, I want to search pets by species, gender, age, vaccination status so that I can filter results | GET /adoptable-pets/search filters by species, city, gender, ageMonths range, vaccinated, adoptionReady, specialNeeds | 2 | High | PETZ_TS_14_AdoptablePetsBrowse | Sprint 4 | To Do
US-027 | NGO Pet Listings | As an NGO rep, I want to create and manage pet listings so that citizens can apply to adopt them | POST /ngo/adoptable-pets requires species; PATCH updates with audit log; POST /archive removes from public browse | 3 | High | PETZ_TS_15_NGOPetListingCRUD | Sprint 4 | To Do
US-028 | NGO Pet Listings | As an NGO rep, I want to upload and manage pet photos so that listings have visual appeal | POST /media accepts JPEG <=20 MB; >20 MB rejected; PATCH /primary sets primary photo; DELETE removes media | 2 | Medium | PETZ_TS_15_NGOPetListingCRUD | Sprint 4 | To Do
US-029 | Adoption Application | As an adopter, I want to start an adoption application so that I can apply for a pet | POST /adoption-applications creates DRAFT; second application for same pet returns 409 | 2 | High | PETZ_TS_16_AdoptionApplication | Sprint 4 | To Do
US-030 | Adoption Application | As an adopter, I want to fill and submit a multi-step application form so that my request is reviewed by the NGO | PATCH /{id}/personal, /lifestyle, /experience, /consent save correctly; POST /submit requires all consents:true; duplicate submit returns 409 | 3 | High | PETZ_TS_16_AdoptionApplication | Sprint 4 | To Do
US-031 | Adoption Application | As an adopter, I want to upload KYC documents so that my identity can be verified | POST /documents with PDF <=5 MB sets verificationStatus:PENDING; >5 MB rejected | 2 | High | PETZ_TS_16_AdoptionApplication | Sprint 4 | To Do
US-032 | Adoption Application | As an adopter, I want to withdraw my application so that I can cancel if my situation changes | POST /withdraw on SUBMITTED sets WITHDRAWN; withdraw on APPROVED returns 409 | 1 | Medium | PETZ_TS_16_AdoptionApplication | Sprint 4 | To Do
US-033 | Adoption Review | As an NGO rep, I want to start reviewing and approve or reject applications so that eligible adopters are selected | POST /review-start sets UNDER_REVIEW; approve requires confirm:true (400 without); reject requires reason (400 without) | 3 | High | PETZ_TS_17_AdoptionReviewAndKYC | Sprint 4 | To Do
US-034 | Adoption Review | As an NGO rep, I want to request clarification and verify KYC documents so that applications are thorough | POST /clarify sets CLARIFICATION_REQUESTED; POST /verify marks VERIFIED; REJECTED requires reason (400 without) | 2 | High | PETZ_TS_17_AdoptionReviewAndKYC | Sprint 4 | To Do
US-035 | Adoption Completion | As an NGO rep, I want to schedule and confirm the adoption handover so that the adoption is officially complete | POST /schedule requires APPROVED status; POST /confirm-handover sets COMPLETED; pet becomes ADOPTED; irreversible | 3 | High | PETZ_TS_18_AdoptionCompletion | Sprint 4 | To Do
US-036 | Adoption Completion | As an NGO rep, I want to record follow-up welfare checks so that adopted animals are monitored | 3 auto-created follow-ups (DAY_7, DAY_30, DAY_90); PATCH /COMPLETED or FLAGGED (concernFlag:true triggers admin) | 2 | Medium | PETZ_TS_18_AdoptionCompletion | Sprint 4 | To Do
US-037 | Adoption Completion | As a user, I want to raise a dispute about an adoption so that welfare concerns are formally addressed | POST /disputes creates OPEN; admin can WARN (RESOLVED) or SUSPEND (account deactivated) | 2 | High | PETZ_TS_19_DisputesAndAdminNGO | Sprint 4 | To Do
US-038 | Admin | As an admin, I want to approve or suspend NGOs so that only trusted organisations operate on the platform | POST /admin/ngos/{id}/verify APPROVE makes listings public; SUSPEND sets active:false | 2 | High | PETZ_TS_19_DisputesAndAdminNGO | Sprint 4 | To Do
US-039 | Admin | As an admin, I want to view adoption KPI metrics and audit logs so that I can monitor platform health | GET /metrics returns totalApplications, approvedCount, completedAdoptions, conversionRate, avgReviewTime; GET /audit-logs paginated; 403 for non-admin | 2 | Medium | PETZ_TS_19_DisputesAndAdminNGO | Sprint 4 | To Do
US-040 | Security | As the platform, I want all protected endpoints to enforce JWT authentication and role-based access so that data is secure | Expired/missing/malformed JWT returns 401; wrong role returns 403; unknown UUID returns 404; empty body returns 400 | 3 | High | PETZ_TS_20_SecurityAndEdgeCases | Sprint 4 | To Do
TOTAL STORY POINTS

## Sprint 4 Backlog
US ID | User Story (Short) | Test Scenarios Covered | Test Cases Covered | SP | Assigned To | Week | Day | Status | Acceptance Criteria Met?
US-001 | OTP send/verify, rate-limit, missed-call | PETZ_TS_01_OTP_Auth | TC001–TC003 | 3 | T1 | Week 1 | D3 | To Do
US-002 | REPORTER JWT on OTP verify | PETZ_TS_01_OTP_Auth | TC003 | 1 | T1 | Week 1 | D3 | To Do
US-003 | Missed-call fallback navigation | PETZ_TS_01_OTP_Auth | TC003 | 1 | T1 | Week 1 | D3 | To Do
US-004 | Full account registration + validations | PETZ_TS_02_Registration_Login | TC004, TC005 | 3 | T1 | Week 1 | D3 | To Do
US-005 | Password login + lockout (423) + 15-min unlock | PETZ_TS_02_Registration_Login | TC006 | 3 | T1 | Week 1 | D3 | To Do
US-006 | Session conversion REPORTER to full account | PETZ_TS_03_SessionAndProfile | TC007 | 2 | T1 | Week 1 | D3 | To Do
US-007 | GET /users/me profile + 401 without token | PETZ_TS_03_SessionAndProfile | TC008 | 2 | T1 | Week 1 | D3 | To Do
US-008 | PATCH profile; verified-flag reset on email/phone change | PETZ_TS_03_SessionAndProfile | TC008 | 2 | T1 | Week 1 | D3 | To Do
US-009 | Password change; old password rejected | PETZ_TS_03_SessionAndProfile | TC009 | 2 | T1 | Week 1 | D3 | To Do
US-010 | Profile photo upload JPEG/PNG <=20 MB; >20 MB rejected | PETZ_TS_03_SessionAndProfile | TC009 | 1 | T1 | Week 1 | D3 | To Do
US-011 | Paginated notifications; unreadOnly filter; unread count | PETZ_TS_04_Notifications | TC010 | 2 | T4 | Week 1 | D3 | To Do
US-012 | Mark-read; mark-all-read; delete; cross-user 403 | PETZ_TS_04_Notifications | TC011 | 2 | T4 | Week 1 | D3 | To Do
US-013 | SOS creation all urgency levels; coordinate bounds; rate-limit | PETZ_TS_05_SOSReportCreation | TC012, TC013 | 3 | T1 | Week 1 | D4 | To Do
US-014 | SOS media upload rules (type/count cap/size) | PETZ_TS_06_SOSMedia | TC014 | 2 | T1 | Week 1 | D4 | To Do
US-015 | NGO registration; one-per-user; unverified hidden from public | PETZ_TS_07_NGO_Registration_Mission | TC015 | 3 | T1 | Week 1 | D4 | To Do
US-016 | Rescue mission lifecycle DISPATCHED to COMPLETED; summary; verify | PETZ_TS_07_NGO_Registration_Mission | TC016 | 3 | T1 | Week 1 | D4 | To Do
US-017 | On-site arrival; assessment; nearby hospital fetch | PETZ_TS_08_OnSiteRescue | TC017 | 3 | T2 | Week 1 | D4 | To Do
US-018 | Hospital alert; emergency booking; handover role guard; release | PETZ_TS_08_OnSiteRescue | TC018 | 3 | T2 | Week 1 | D4 | To Do
US-019 | Public hospital browse; distance sort; verified-only | PETZ_TS_09_HospitalDiscovery | TC019 | 2 | T2 | Week 1 | D4 | To Do
US-020 | Hospital search filters (city/serviceType/openNow); full profile | PETZ_TS_09_HospitalDiscovery | TC020 | 2 | T2 | Week 1 | D4 | To Do
US-021 | Slot creation HH:mm:ss; recurring; blackout behaviour | PETZ_TS_10_SlotManagement | TC021, TC022 | 3 | T2 | Week 1 | D5 | To Do
US-022 | Lock-confirm booking; lock expiry; double-booking prevention | PETZ_TS_11_BookingFlow | TC023, TC024 | 3 | T2 | Week 1 | D5 | To Do
US-023 | Cancel/reschedule; attend; complete (clinical notes); no-show | PETZ_TS_12_AppointmentLifecycle | TC025 | 3 | T2 | Week 1 | D5 | To Do
US-024 | Admin: approve/reject/disable hospital; booking cancellation; 403 | PETZ_TS_13_HospitalAdminActions | TC027 | 3 | T4 | Week 2 | D6 | To Do
US-025 | Public pet browse; ADOPTED/ARCHIVED excluded; distance sort; cap | PETZ_TS_14_AdoptablePetsBrowse | TC028 | 2 | T3 | Week 2 | D6 | To Do
US-026 | Pet search multi-filter (species/city/gender/age/vaccinated) | PETZ_TS_14_AdoptablePetsBrowse | TC029 | 2 | T3 | Week 2 | D6 | To Do
US-027 | NGO pet listing CRUD + archive; audit log | PETZ_TS_15_NGOPetListingCRUD | TC030 | 3 | T2 | Week 2 | D6 | To Do
US-028 | Pet media upload; set-primary; delete | PETZ_TS_15_NGOPetListingCRUD | TC031 | 2 | T2 | Week 2 | D6 | To Do
US-029 | Adoption application start DRAFT; one-active-per-pet 409 | PETZ_TS_16_AdoptionApplication | TC032 | 2 | T3 | Week 2 | D6 | To Do
US-030 | Multi-step form (personal/lifestyle/experience/consent); submit rules | PETZ_TS_16_AdoptionApplication | TC033 | 3 | T3 | Week 2 | D7 | To Do
US-031 | KYC document upload (PDF <=5 MB); >5 MB rejected | PETZ_TS_16_AdoptionApplication | TC034 | 2 | T3 | Week 2 | D7 | To Do
US-032 | Withdraw SUBMITTED (OK); withdraw APPROVED (409) | PETZ_TS_16_AdoptionApplication | TC034 | 1 | T3 | Week 2 | D7 | To Do
US-033 | NGO review-start; approve (confirm guard); reject (reason required) | PETZ_TS_17_AdoptionReviewAndKYC | TC035 | 3 | T1 | Week 2 | D7 | To Do
US-034 | Clarification request; KYC verify VERIFIED/REJECTED (reason required) | PETZ_TS_17_AdoptionReviewAndKYC | TC036 | 2 | T1 | Week 2 | D7 | To Do
US-035 | Handover schedule (APPROVED required); confirm-handover chain; irreversible | PETZ_TS_18_AdoptionCompletion | TC037 | 3 | T3 | Week 2 | D7 | To Do
US-036 | Follow-up COMPLETED and FLAGGED (admin triggered) | PETZ_TS_18_AdoptionCompletion | TC038 | 2 | T3 | Week 2 | D8 | To Do
US-037 | Raise dispute; admin WARN/SUSPEND resolution | PETZ_TS_19_DisputesAndAdminNGO | TC039 | 2 | T1 | Week 2 | D8 | To Do
US-038 | Admin NGO APPROVE/SUSPEND; listings visibility | PETZ_TS_19_DisputesAndAdminNGO | TC040 | 2 | T4 | Week 2 | D8 | To Do
US-039 | Adoption metrics (KPIs + date range); audit log filters; 403 | PETZ_TS_19_DisputesAndAdminNGO | TC040 | 2 | T4 | Week 2 | D8 | To Do
US-040 | JWT expired/missing/malformed 401; wrong role 403; 404/400 edge cases | PETZ_TS_20_SecurityAndEdgeCases | TC041, TC042 | 3 | T4 | Week 2 | D9 | To Do
SPRINT 4 TOTAL STORY POINTS

## Tester Capacity
Tester | Role / Module Focus | Week 1 Tasks | Week 2 Tasks | Total SP | User Stories | Test Cases
T1 – Tester 1 | Auth · SOS · Profile · NGO Rescue · Adoption Review | US-001–010, US-013–016 TC001–TC016 Scenarios TS_01–TS_08 | US-033–034, US-037 TC033–TC036, TC039 Regression and defect retest | 36 | US-001 to 010, 013–016, 033–034, 037 | TC001–TC016, TC033–TC036, TC039
T2 – Tester 2 | Hospitals · Booking · On-Site Rescue · NGO Pet Listings | US-017–023 TC017–TC025 Scenarios TS_08–TS_12 | US-027–028 TC027–TC031 Regression | 34 | US-017 to 023, 027–028 | TC017–TC025, TC027–TC031
T3 – Tester 3 | Adoption Flow – Browse through Completion | US-025–026 Scenarios TS_14–TS_18 authoring | US-025–026, US-029–032, US-035–036 TC028–TC038 | 32 | US-025, 026, 029–032, 035–036 | TC028–TC038
T4 – Tester 4 | Cross-Cutting · Admin · Security · Notifications | US-011–012, US-019–020 TC010–TC011, TC019–TC020 Scenarios TS_04, TS_09, TS_13, TS_19–20 | US-024, US-038–040 TC027, TC040–TC042 Accessibility and telemetry checks | 36 | US-011, 012, 019, 020, 024, 038–040 | TC010–TC011, TC019–TC020, TC027, TC040–TC042